## Requirements
Req ID | Requirement Description | Type | Priority | Priority Reasoning | Dependent On | Implementation | Test Case | Status | Progress % | Actions | Notes
FR-1 | Students and teachers have individual accounts with different signup flows | Functional | High | Foundational requirement; all system functionality depends on authenticated users | Cognito User Pool | Cognito auth + signup triggers | TC-AUTH-01 | Implemented | 100
FR-2 | Teachers can manage classrooms and reset student accounts | Functional | High | Essential for classroom control and daily teacher operations | FR-1 | Teacher dashboard + admin APIs | TC-TEACH-01 | Implemented | 100 |  |  | Not Started
FR-3 | Secure login with minimal personal data | Functional | High | Required for legal compliance, privacy protection, and user trust | FR-1 | Cognito + DynamoDB schema | TC-AUTH-02 | Implemented | 100 |  |  | In Progress
FR-4 | Students have 2D avatars with visual progression | Functional | Medium | Supports student engagement and long-term motivation but not required for core system operation | FR-7 | Avatar + player state system | TC-AV-01 | In Progress | 90 | implement the tables and api |  | Implemented
FR-5 | Avatar roles with abilities restored on weekends | Functional | Medium | Adds gameplay depth; can be implemented after core mechanics without blocking usage | FR-7 | Ability engine + EventBridge | TC-AV-02 | In Progress | 60 | heart system in place. need to work on implementing abilities mechanics | disccussed the basic logic for ech avatar | Verified
FR-6 | Cosmetic items purchasable and stored in inventory | Functional | Low | Purely cosmetic; does not affect learning or system stability | FR-14 | Inventory + shop tables | TC-SHOP-01 | Implemented | 100 |  |  | Deferred
FR-7 | Core XP, gold, and hearts mechanics | Functional | High | Core gameplay loop; without this the platform has no functional value | FR-1 | PlayerStates + reward ledger | TC-GAME-01 | Implemented | 100
FR-8 | Side quests displayed on a map | Functional | Low | Primary mechanism for delivering assignments in a gamified format | FR-7 | Quest templates + instances | TC-QUEST-01 | Deferred |  |  | list will suffice for now
FR-9 | Boss battles representing exams | Functional | High | Critical feature that differentiates the platform from standard classroom tools | FR-7 | Boss battle system | TC-BOSS-01 | In Progress | 80 | implement guild base mode
FR-10 | Random daily events | Functional | Medium | Enhances engagement but not required for basic classroom functionality | FR-7 | Daily events + scheduler | TC-EVENT-01 | Deferred | 50 | base for questions and quests has been completed, need to difine the logic | not core mechanic
FR-11 | XP and gold rewards for tasks | Functional | High | Directly tied to student motivation and progression | FR-7 | RewardTransactions | TC-REWARD-01 | Implemented | 100
FR-12 | Teachers can issue manual rewards and penalties | Functional | Medium | Necessary for real-world classroom discipline and flexibility | FR-11, FR-2 | Teacher controls + ledger | TC-REWARD-02 | Implemented | 100
FR-13 | Partial rewards for group work | Functional | Medium | Improves fairness in group-based activities but not blocking core use | FR-11 | Reward calculation logic | TC-REWARD-03 | Deferred
FR-14 | Item shop for spending gold | Functional | Medium | Supports in-game economy but can follow core mechanics | FR-7 | Shop + inventory UI | TC-SHOP-02 | Implemented | 100
FR-15 | Students grouped into guilds | Functional | High | Fundamental to collaboration-based classroom design | FR-7 | Guild + membership tables | TC-GUILD-01 | Implemented | 100
FR-16 | Limited student leaderboard, full teacher view | Functional | High | Required to balance competition while preventing negative student comparison | FR-7 | Leaderboard GSI | TC-LB-01 | Implemented | 100
FR-17 | Guild members can help each other | Functional | Medium | Enhances teamwork but depends on guild system being present | FR-15 | Ability targeting logic | TC-GUILD-02 | Deferred
FR-18 | Teacher dashboard for quests, bosses, events | Functional | High | Central control interface for teachers; required for system usability | FR-2 | Teacher UI | TC-TEACH-02 | Implemented | 100
FR-19 | Quest templates to save setup time | Functional | Medium | Reduces teacher setup time but system can function without it | FR-8 | QuestTemplates | TC-QUEST-02 | Implemented | 100 | quest template is ready, need to populate the base quests. future: implement download/upload of quests
FR-20 | Demo setup for classroom projection | Functional | Low | Helpful for demonstrations and onboarding but not required for core use. To provide example flow for students/teacher | FR-18 | Demo flag + mock users | TC-DEMO-01 | In Progress | 80 | partially, users are ready, easy to populate
FR-21 | Parent view-only access (future) | Functional | Low | Future-facing feature; explicitly out of MVP scope | FR-1 | ParentProfiles | TC-PARENT-01 | Deferred |  |  | Out of MVP
NFR-1 | Web-based platform for Chromebooks | Non-Functional | High | Required for target device compatibility in schools |  | React + browser support | TC-NF-01 | Implemented | 100 |  | designed web layout
NFR-2 | Runs on low-end school hardware | Non-Functional | High | Ensures accessibility across real classroom hardware environments | NFR-1 | Performance optimization | TC-NF-02 | Implemented | 100 |  | everything critical runs on cloud due to API calls
NFR-3 | Cloud-hosted secure backend | Non-Functional | High | Core infrastructure requirement; system cannot operate without it |  | AWS serverless stack | TC-NF-03 | In Progress | 70 | complete the verification and authentication before each API call | works
NFR-4 | Scalable across classrooms and schools | Non-Functional | High | Required to support growth beyond a single classroom | NFR-3 | Multi-tenant design | TC-NF-04 | In Progress | 90 | finish ready to go business model | AWS Serverless is very scalable
NFR-5 | 99.9% uptime during school hours | Non-Functional | Medium | Reliability expectation but not directly affecting MVP feature set | NFR-3 | AWS managed services | TC-NF-05 | Implemented | 100 | AWS guarntees
NFR-6 | Core actions under 2 seconds | Non-Functional | Medium | Performance goal; important for experience but not blocking MVP | NFR-3 | API + caching | TC-NF-06 | Implemented | 100 | learn caching is the next step to make it run faster | AWS implementation makes it fast
NFR-7 | Support 30+ concurrent students | Non-Functional | Medium | Scalability expectation; becomes critical at classroom deployment scale | NFR-3 | Load-tested APIs | TC-NF-07 | Implemented | 100 |  | Serveless design allows flexibilty
NFR-8 | Real-time sync under 1 second | Non-Functional | High | Required for real-time classroom feedback and control | NFR-3 | AppSync subscriptions | TC-NF-08 | Implemented | 100 | AWS structure
NFR-9 | Encrypted communication and hashed passwords | Non-Functional | High | Mandatory for security, privacy, and compliance |  | HTTPS + Cognito | TC-NF-09 | Implemented | 100 | Cognito
NFR-10 | Daily backups and 1 hour recovery | Non-Functional | Medium | Operational resilience requirement; important but not user-facing | NFR-3 | DynamoDB backups | TC-NF-10 | Deferred |  | implement table backup everyday