## Sheet1
Module | Requirement ID | Feature | Current Status | Risk | Test Level | Evidence Source
Authentication | FR-1 | Teacher signup/login | Implemented | High | Unit | auth tests, Cognito triggers, frontend login
Authentication | FR-1 | Teacher forgot password | Implemented | Medium | Unit | auth tests
Authentication | FR-1, FR-8 | Student join class with code | Implemented | High | Unit | classEnrollments tests, frontend signup
Authentication | FR-1, FR-8 | Teacher-only access enforcement | Partially implemented | Critical | Unit | shared/auth.ts, TODOs in handlers
Authentication | — | API Gateway JWT authorizer | Not implemented | Critical | None | auth TODO
Authentication | — | Teacher approval workflow | Not implemented | Medium | None | postConfirmation TODO
Class Management | FR-1, FR-6 | Teacher creates class | Implemented | High | Unit | classes tests
Class Management | FR-6 | Class deactivation | Implemented | Medium | Unit | deactivate handler
Class Management | FR-8 | Student enrollment lifecycle | Implemented | High | Unit | classEnrollments tests
Quest Management | FR-6, FR-9 | Create quest template | Implemented | High | Unit | questTemplates tests
Quest Management | FR-6, FR-9 | Create quest questions | Implemented | High | Unit | questQuestions tests
Quest Management | FR-6, FR-9 | Assign quest to class | Implemented | High | Unit | questInstances tests
Quest Management | FR-9 | Scheduled quest activation | Implemented | Medium | Unit | scheduled Lambda
Quest Submission | FR-3, FR-4 | Filter quests by class | Implemented | High | Unit | list-by-class
Quest Submission | FR-3, FR-4 | Submit quest response | Implemented | High | Unit | response tests
Quest Submission | FR-3, FR-4 | Auto grading | Implemented | High | Unit | grading logic
Quest Submission | FR-4 | Attempt tracking | Implemented | Medium | Unit | attempt tests
Quest Submission | FR-4 | Reward state linkage | Implemented | High | Unit | reward state handlers
Progression | FR-3, FR-4 | XP/gold/hearts update | Implemented | High | Unit | playerStates tests
Progression | FR-4 | Prevent duplicate rewards | Implemented | High | Unit | rewardTransactions tests
Progression | FR-4 | XP leveling formula | Implemented | Medium | Unit | xp-progression
Reward Milestones | FR-4 | Create reward milestones | Implemented | Medium | Unit | milestone tests
Reward Milestones | FR-4 | Default rewards seeding | Implemented | Medium | Unit | default rewards
Reward Milestones | FR-4 | Student reward claims | Implemented | High | Unit | reward claims tests
Guild System | FR-5 | Create guilds | Implemented | Medium | Unit | guild tests
Guild System | FR-5 | Manage guild membership | Implemented | Medium | Unit | membership tests
Teacher Controls | FR-6, FR-8 | Set student password | Implemented | High | Unit | student profile tests
Teacher Controls | FR-6, FR-8 | Edit student username | Implemented | High | Unit | validation + Cognito sync
Teacher Controls | FR-6 | Edit XP/gold/hearts | Implemented | High | Unit | playerStates
Leaderboard | FR-5, FR-6 | Leaderboard ranking | Implemented | Medium | Unit | leaderboard handler
Boss Battle | FR-3, FR-5 | Template/question CRUD | Implemented | High | Unit | boss templates/tests
Boss Battle | FR-3, FR-5 | State machine | Partially implemented | Critical | Unit | 31 failing tests
Boss Battle | FR-3, FR-5 | Participants management | Implemented | Medium | Unit | participants tests
Boss Battle | FR-3, FR-5 | Question plans | Implemented | Medium | Unit | plan tests
Boss Battle | FR-3, FR-5 | Answer tracking | Partially implemented | High | Unit | TODOs present
Boss Battle | FR-3, FR-5 | Results computation | Implemented | High | Unit | bossResults tests
Boss Battle | FR-3, FR-5 | Real-time subscriptions | Implemented | Medium | Unit | AppSync resolvers
Boss Battle | FR-3, FR-5 | Snapshots/history | Implemented | Low | Unit | snapshot tests
Boss Battle | FR-5 | Frontend play flow | Partially implemented | High | Manual | bossFight.tsx
Shop/Inventory | — | Shop items CRUD | Implemented | Medium | Unit | shopItems tests
Shop/Inventory | — | Shop listings | Implemented | Medium | Unit | listings tests
Shop/Inventory | — | Inventory tracking | Implemented | Medium | Unit | inventory tests
Shop/Inventory | — | Purchase flow | Implemented | High | Manual | frontend logic
Shop/Inventory | — | Equipped items | Implemented | Medium | Unit | equippedItems tests
Avatar System | — | Avatar templates | Implemented | Low | Unit | avatarBases tests
Avatar System | — | Player avatars | Implemented | Low | Unit | playerAvatars tests
Image Upload | — | Presigned URL generation | Implemented | Medium | Unit | upload tests
Users | — | User mapping table | Implemented | Low | None